## Program
25 May 2008 (Sun), 8:30am-2:00pm - Contests & Closing Ceremony (last updated by Chin Mei Har 15 May 2008)
Venue: SuntecCity Theatre , Capacity: 580
Attire: Business
Contests (8:30am-11:45pm)
Time | Duration | Activities/Role Bearers for Contests | by | Remarks
(mins)
8:00am | 14 | Reception/ Registration | Linda Neo, in charge | · To check delegates' passes and attendee's tickets for CCC.
8:05am | 24 | Chief Judge: Poh Kim Siong to brief Timers: Chan Boon Hwee, Monica Goh. Tally Counters: Esther Heng, Albert Lim and Catherine Goh, SAAs: John Tan, Eng Zee Lin and Dennis Wang. Contest Chair: Goh Wei Koon & Neil Sy to get Contestants to draw lots for their speaking positions. Prizes i/c:Chin Mei Har, Eliz | Dayal, Golam and Elizabeth - Floor Managers | · Ensure – mic, audio & video, CD/DVD/VCD, flag stand (for flag ceremony)
· seats reservations (officers, VIPs, contestants)
· Ensure power point ok. Rose & team to liaise with Suntec staff/Logistics who operates PowerPoint
· Contestants will be testing mics
8:15am | 19 | Music setup | KC Goh
8:25am | 1 | Announcement of Contest-to-start | James Lim & Joanne Koo | · MCs to ask everybody to be seated
International Speech and Table Topic Contests
8:30am | 10 | Contests start and Opening by MCs Contest Master speaks | 2 MC to introduce DG Michael Wee,DTM as Contest Master | · James Lim & Joanne Koo
Contest Master: DG Michael Wee
8:40am | 10 | Briefing by Contest Chair | Goh Wei Koon, DTM
8:50am | 75 | International Speech Contest. Tally counters to collect ballots and accompany Chief Judge out of Theatre to tally ballots. | Goh Wei Koon, DTM | Goh Wei Koon. Tally counters are Esther Heng, Albert Lim and Katherine Goh.
10:05am | 20 | Break
10.25am | 5 | Reopening of Contest by MCs. Contest Master speaks | 2 MCs to introduce Michael Wee, Contest Master | MCs to get everyone settled. Contest Master: DG Michael Wee
10:30am | 10 | Briefing by Contest Chair | Neil Sy, ACB | · KC prepares 10-secs music when Neil Sy is coming up on stage
10:40am | 40 | Table Topic Contest | Neil Sy, ACB | · SAAs : John Tan, Eng Zee Lin and Dennis Wang will accompany contestants outside. Mobile phones will be removed.
11:15am | 15 | Air Time. MCs to take over control of lectern | 2 MCs | Both MCs will script how they intend to entertain the audience for duration of 15 mins
11:30am | 10 | Announcement of Results Contest Chairs to give out certificates of participation to Contestants only.Presenters: Chin Mei Har & Elizabeth Thorarajoo | Goh Wei Koon, DTM & Neil Sy ACB | · KC prepares 10-secs music when Michael Wee is coming up on stage
|  |  | Michael Wee, DTM to give away the prizes and Challenge Trophies | · KC will prepare triumphal music when announcing winners
11:45am | - | Contests end | Goh Wei Koon, DTM | · Pass the stage to MCs of the Closing Ceremony
Closing Ceremony (11:45am to 12:33pm) |  |  | DTM
Time | Duration | Activities | by | Remarks
(mins)
11:45am | 1 | MCs to begin the Closing Ceremony | James Lim | · KC prepares 10-secs music when James and Joanne come up on stage
|  |  | Joanne Koo | · MCs to thank Contest Chair, Goh Wei Koon.
11:46am | 6 | Fast, vibrant Latin Dance Number | James Tan | KC to prepare fast 15-sec music for Dancers to run down the auditorium. James Tan must pass actual dance CD to Kheng Chuan by 19 May 08.
11:47am | 5 | MCs to introduce - Playback of Convention photos (last two days) | Rose & Team | · Mei Har will talk to photographer to show photos from CD/ DVD. Mei Har has confirmed that the song, 'Friends for Life' by Sarah Brightman will be played. KC to make available the CD.
· KC to ensure it is played.
11:52am | 7 | Speech by Convention Chair/co-chair | Tay Yiang Ping,DTM & Mike Rod, DTM | · KC to prepare 10-secs music when YP&Mike Rod are coming up on stage
· Mei Har to re-confirm with YP [In particular the time is cut to 7 mins]
11:59am | 2 | Flag Ceremony | YP & MR (Convention Chairs) | · MCs ask YP & MR remain onstage
· MCs invite Tay Yiang Ping and Mike Rod on stage.
|  |  | · Michael Rodrigues, DTM (co-Chair) | · KC to prepare upbeat background music
· Tay Yiang Ping and Mike Rod to wave the flag and put it in flag stand
12.01pm | 7 | Promotion of next Annual Convention in Hongkong | Organising Chair: Teresa Lee | · KC to prepare music for Teresa Lee
12:08am | 7 | Promotion of Semi-Annual Convention in Singapore | Organising Chair: Cynthia Chan, DTM | · KC to prepare 10-secs music when Cynthia is coming up on stage
·
12:15pm | 8 | Moments of Appreciation Presentation of Certificates of Appreciation and Plaques to the MAD org committee. Photograph-taking on stage. | · District Governor,Michael Wee, DTM | · KC to prepare 10-secs music when Michael Wee and others are coming up on stage
|  |  | · Lt Governor Education, Goh Wei Koon, DTM | · Joanne to get the Convention committee members' list from Yiang Ping and Mike Rod before 16 May 08.
|  |  | · Lt Governor Marketing, Neil Sy | · Mei Har to inform all event chairpersons in advance by 19 MAY 08 to get their team members to go on stage
|  |  | · Heads of sub- Committee members | · Floor Manager (Elizabeth) helps line up people on stage as they move up (to ask other SAAs to help
|  |  | · Heads of sub sections | · Michael Wee to present plaques to the heads of Sub sections.(Mei Har to remind YP to prepare the plaques by end of April).
|  |  | · Convention Chair and Co-Chair YP & Mike Rod | · KC to prepare energetic music once MCs finish announcing names of Heads of sub-sections.
· Michael, Wee Koon and Neil to shake hands with Heads of sub-sections- Opening, Closing, Gala Welcoming, Breakout,Tresurer, Secretariat, Secretary4 club presidents and Neil, Irene
· Michael, Wei Koon and Neil to take a group photos with chairs and all helpers
· SAA to lead helpers to go off stage after taking group photos
12:23pm | 5 | Closing Song | · Michael Rodrigues, DTM (co-Chair) to lead in singing of song. He invites all MAD committee members to join him on stage to sing 'Friends for Life.' | · Mei Har has confirmed the closing song (Friends for Life by Sarah Brightman). KC will prepare VCD. KC to check if MP3 can be used in Suntec Theatre..
|  | half light for whole room and the song starts | Michael Wee, DTM, District Governor & top DL to stay on | · Rose to confirm lighting arrangement with her team members.
stage for closing song.
Turn on light after the song
12:28pm | 5 | Closing remarks & | Michael Wee, DTM, District Gov | Mei Har to remind DG to get speech ready for occasion.
Adjournment of Convention
|  | Off-stage announcement of farewell lunch | MCs -James and Joanne to invite all delegates to lunch in Suntec. | · Farewell lunch
Farewell Lunch (12:33pm to 2:00pm)
12:33pm | 90 | Farewell Lunch – all together | MCs- Ng Cher Khim & Cheng Jia Yi to prepare Lunch-time Prog. They are ready and waiting to welcome delegates | Lucky Draw / Further Promotion of Semi Annual Convention in November2008.Cher Khim to give last min check that mic is working well.
Venue: Concourse Level 3 Suntec Convention Hall
2:00pm | - | Good-bye
Notes:
· Music & Video related – Contact Andy Yip (PTH TMC) |  | ontact Goh Kheng Chuan at HP: 90022959
· Contest to be conducted by District, they prepare trophies, judges and certificates
· Rehearsal being arranged. |  | Chin Mei Har to remind all role bearers | by 13 May 2008.

## Appointment
Please refer to key persons and contact details in the next page
Key persons and contacts
Roles | Name | Key responsibilities | Contact No & Email address
Closing Ceremony Chair | Chin Mei Har | · Overall in-charge of full Sunday's prog from 8-2pm | (65)97220747
|  | · Work with Contest Chair regarding the Role Bearers for the Contests | ipccmh@singnet.com.sg
· Assist the Floor Managers
MCs | James Lim | James & Joanne are the MCs for CCC while Ng Cher Khim & Cheng Jia Yi are the MCs for Farewell lunch segment. | (65)97937085-Joanne Koo
| Joanne Koo |  | (65)91291665 - James Lim
| Ng Cher Khim |  | (65)98390857-Ng Cher Khim
| Cheng Jia Yi |  | (65)94389953-Cheng Jia Yi
Floor Manager | Elizabeth T | Ensure smooth movement of award recipents for closing ceremony.Contest: Elizabeth with Mei Har are in-charge of Prize table | (65)96817747-Elizabeth
(Contests) | Dayal Khemlani | · Reserve seats for District Officers, VIPs and Contestants | (65)91051013-Dayal
| Heru Kasuma | · Ensure functioning of Mic, sound and video systems; music & video CDs are in order | (65)97462702-Heru
| Yeo Chai Tun | · to instruct volunteers to move audience to the seats nearer the stage if needed | (65)93886220-Chai Tun
| Linda Neo | To man the reception table.To distribute Contest Prog & Evaluation Forms | (65)96187626-Linda Neo
Audio & Video | Goh Kheng Chuan/ Ryan Lim | · Audio & Video | (65)90022959- Goh Keng Chuan (65)97688072-Ryan Lim
Logistic in-charge | Rose & Team | · Venue logistics | (65)96370929-Rose Ho
Theatre in charge | Rose & Team |  | (65)96370929-Rose Ho
Photography | Professional | · Video Shooting and photography - to provide KC with digital pics for Playback of Convention Events | (65)91477630-William Han
· Contests co-ordination
Convention Chair | Tay Yiang Ping DTM |  | yptay@starhub.net.sg
(65)96221803
Co-Chair | Michael Rodrigues DTM |  | mikerod@singnet.com.sg
District Governor | Michael Wee, DTM |  | waterdragon@pacific.net.sg
Contest Chair | Goh Wei Koon, DTM |  | weikoon.goh@belden.com (65)92307617 (65)96640771
Next Annual Convention Chair | Teresa Lee | Organising the next Annual Toastmasters Convention 2009 in Hongkong | fly.hkconvention09@gmail.com,tpclee@gmail.com
Semi-Annual Convention Chair | Cynthia Chan | Chair,Semi-Annual Convention, S'pore at YWCA, Fri 21 Nov to Sat 22 Nov 2008. | CynthiaChanSL@Lifeisgreat.com.sg (65)9875177
Cynthia.oac@pacific.net.sg