## Editorial
MAD EDITORIAL TEAM TIME-LINE
Month | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01
Essay Competition | Confirmed Judges | Launched @ COT, Closing Date : 31 Mar 08 |  | Editing | Award of Prizes
Souvenir Magazine Design | Cover Design & Theme/Sections
Collection of Articles - Guest of Honour, IWC, District Officers, Write-ups on Speakers,etc | Those assigned please take note of deadline ie. 29 Feb 2008
Programme | Final | All Events Program
Collection of Advertisements | Collection of Advertisements Deadline : 29 Feb 08
Editing
Printing
Delivery of Souvenir Magazine
MAD EDITORIAL TEAM
Chief Editor | Kris Tay
Assistant Editor | Albert Lim
Advertisements IC | Lynda Neo
Editors for Articles | Cheng Chia Yi & Edward Ma