MAD Team Leader Feedback Form

1.     Team :

MAD Convention Opening Ceremony Subcom

2.     Team Leader:

Aziz Mustajab, DTM

3.     Team Members:

Jeshua S Judah, Ruby Lai, Lynda Neo, Esther Heng, Albert Lim, Keh Toh, Ashley He, Laksha Mehta

4.     How many Team meetings before Convention?:

Four subcom meetings.  Separate briefings for Emcees.  Regular communication via emails.

5.     How many Team members or Volunteers did you actually need at Convention?

8-10.

6.     What were your Team’s expense? Please provide details.

a. Memento for Guest-of-Honor.

b. Allowance for Dikir Barat traditional group = S$350.00

c. Refreshment break

(All claims settled.)

7.     What supplies did you order or bring? (e.g. Secretariat brought Printer, Cartridges, Staples, scissors…; Logistic: Signboard…):

Nil.

8.     In your area of Team Leadership responsibility, what worked well?:

Friendly persuasion.  Value the team members' contributions.  Infuse confidence.

9.     In your area of Team Leadership responsibility, what didn’t work so well?

Assuming that EVERYTHING will turn out according to plan.

10. Did you receive sufficient support from the Top Officers, Organising Chair, Co-Chair and/or other Teams, please give detail comments.

Absolutely.  Everyone wanted the Convention to be the best ever, the MADdest ever.

11. Did you feel that your work was appreciated and valued?

Yes, very much so.

12. What do you think would improve efficiency in the Convention Planning Process.

All subcom leaders should attend main committee meetings and present their progress reports to generate feedback and further discussions.

13. Do you need to contact Suntec Officers, please describe.

No.  Problems were settled at site visits prior to Convention.

14. Please give comment of some positive and constructive comments that you want to share with Suntec.

Nil.

15. Please attached copies of any forms, timeline, manpower assignment, Programme … that your team developed or used.

Refer to attachments.

16. Anything else that you feel would be helpful and useful for the next team leaders who will follow in your footsteps.

a.  Prepare for last-minute changes and instructions from the top.

b.  Make sure that team members really understand what they are supposed to do.  Request for progress reports.

Thank you in advanced for your contribution, it was a great pleasure to work with you and to get to know you.