MAD Team Leader Feedback Form

- Team : Secretariat

- Team Leader: Doreen

- Team Members: Pak Fee, Ashley, Tian Teang, Edwin, Yeow Kian

- How many Team meetings before Convention? 3 official, more com via mails

- How many Team members or Volunteers did you actually need at Convention?

a) dependant on the numbers of delegates and materials to be packed

b) packing – 20+ of which 6 were volunteers

- What were your Team’s expense? Please provide details.

a. Convention Bag  - $2,140.00

b. Lanyard & holder - $   802.50

c. Name Tag            - $   602.00

- What supplies did you order or bring? (e.g. Secretariat brought Printer, Cartridges, Staples, scissors …)

a. printer is a must

- In your area of Team Leadership responsibility, what worked well?

        - selecting the right person for the job

        - delegation of work

        - team member very cohesive

        - sharing of experience & knowledge

        - listen to ideas

        - advice & support from others

Each team member fulfilled his/her responsibility under his/her charge

i) PF: Process of Packing was worked out and team members were briefed. On packing day, he took control of the whole process.

Volunteers and other committee members were informed of packing time

Suppliers, printer & sponsors were informed of the delivery time

ii) TT: Delegation list & co-ordination with L&E on the pre-registration list. Design of icon for name tag

iii) Ashley, YK, Edwin : Manning the Registration counters, lost & found

iv) Doreen: Liaison with supplier for bag and printer for Name tag, program & workshop coupons

- In your area of Team Leadership responsibility, what didn’t work so well?

a.      Delayed delivery of name card, programe

b.      Due to missing key information, that is 'Name, Club and Division" in the 	pre-registration list v the registration list had made insertion of the coupons 	into name tag difficult.

c.   Workaround solution was very manual labour intensive and longer hours             were taken to complete the work.

d.   As a result the whole process was completed around 9 pm

e.   Thanks to the support and patience of the remaining helpers who stayed till

9pm to complete the work. Esp thanks to Michael

- Did you receive sufficient support from the Top Officers, Organising Chair, Co-Chair and/or other Teams, please give detail comments.

a.  Thanks to YP & Michael for  supporting my decision rejecting one delegate request to allow some to take over the Dinner without “surending” her Name Tag for admission.

b.  IPDG, Kim Siong – supporting my decision to allow a transferee admission into the Mandarin contest which was abt to start, while we verified her transferred case.

c. One delegate who left her Name Tag in the hotel, we issued her a temp Name Tag for admission to Welcome Dinner

11. Did you feel that your work was appreciated and valued?

a. a few delegates did come up to me & commented that Secretariat had done a good job

b. the credit should go to my team members who had gone beyond their call of duty to serve the delegates

c.   Just to quote a few

i)  TT helped one delegate to Suntec admin area for First Aid facility

ii)  YK helped the Indian TM to set up the place

iii)   Edwin helped to man the Speaker’s counter for sale of product

- What do you think would improve efficiency in the Convention Planning Process?

Learning Point for

a. Packing

i)   We were partially responsible for the delay in the delivery Name Tag cos we gave the printer 1 day lead time instead of the agreed 4 days due to changes

ii) Critical to have firmed cut off date so that sufficient lead time is given to printer for printing. Any last min changes to be taken care by Secretariat.

iii)  Pre-registration list v Registration list must contain similar key information

b. Registration

i)    Signage is very important esp those place on tables indicating the Division served. It has to be large & high enough so that it would not be blocked from view by the surrounding crowd at the counters

ii)   The operating hour for delegate registration and workshop registration should be concurrent so as not to inconvenient the delegates.

iii)  If admission to Dinner is by Name Tag & operating hr is till 5pm, Secretariat has to plan how to serve this grp of delegates. We set up a mini counter at the entrance of Dinner venue. Only inconvenience to delegates was that they had to collect their convention bags the following day.

iii)  We overlooked the provision of First Aid box.

iv) Safety Evacuation … Announcement of fire exit route

v)  Announcement of Lost items … suggest that the announcement should be made more frequent

- Do you need to contact Suntec Officers, please describe.

a. yes – when Mandarin TM feedback that they could not set up their power point

- Please give comment of some positive and constructive comments that you want to share with Suntec

a. Jun was very helpful, attended to every of our call of needs

b. Even expanded effort to help look for lost handphone

c.  Assist in transporting goods from lift to room 207

d.  YK – technician to help the Indian TMC to set up the sound system.

admin staff to log in to Yahoo mail so that he could use the internet

to send urgent report to his boss

trolley from the kitchen staff to ferry our cactus to the ballroom

- Please attached copies of any forms, timeline, manpower assignment, Programme … that your team developed or used.

- Anything else that you feel would be helpful and useful for the next team leaders who will follow in your footsteps.

a.  visit the site of convention

Thank you in advanced for your contribution, it was a great pleasure to work with you and to get to know you.