## Presn Agenda
TOASTMASTERS INTERNATIONAL DISTRICT 80 ANNUAL CONVENTION
Date: | 23 to 25 May 2008 (Friday to Sunday)
Venue: | SUNTEC Singapore International Convention & Exhibition Centre
Hospitality Masterplan
Date | Time | Program | Room | Logistics Requirements | Contact Person | YP
22-25 May | 0800-1700hrs | Pre-Convention Preparation | L2 Rm 207 | Secretariat Room Setup & Operations. Need additional 4 tables | Doreen Neo
& chairs outside the Meeting Room 207
|  |  |  | 1. 600 pens & writing pads to be delivered on 22 May am to the rm | Wen Jun/Suntec
|  |  |  | 2. Packing of Convention Bags/Lanyards | Doreen Neo & Team
|  |  |  | 3. Workshops Registration | Doreen Neo & Team
|  |  |  | 4. Carpark & Meal Coupons Issuance | Jenny/Doreen
2008-05-23 | 0830-1230hrs | District 80 Exco & Council Meeting | Rm 208/209 | Coffee-Break @ 10:30am | Wen Jun/Suntec
|  |  |  | No. of pax 60 (Catering inside the rooms) | Jenny Au | Remarks: Well control.
|  |  |  | Need 3 tables & chairs for registration outside meeting room | Wen Jun/Suntec
|  |  |  | Layout for Exco Members: 8 | Wen Jun/Suntec | Parliamentarian = total 8
|  |  |  | Require 50 additional chairs (contingency) | Wen Jun/Suntec
|  |  |  | 3 Microphones - 1 wired & 2 wireless | Wen Jun/Suntec | 1 standing Mic for Candidate and Audience
|  |  |  | Nameplates for the Exco Members | Jenny Au/Rose
|  |  |  | Projector/Screen Required & Signage | Rose
2008-05-23 | 1230-1330hrs | Exco & MAD Team Lunch | - | Lunch Coupon | Yiang Ping
|  |  |  | Guest Speakers Lunch Arrangement | Jenny Au
2008-05-23 | 1400-1700hrs | English Workshop | Rm 208/209 | English Workshop; Anne Barab, DTM (Accredited Speaker) | Yeo Chai Tun
|  |  |  | Coffee-Break @ 3:15pm (No.of pax 350)* | Wen Jun/Jenny
|  |  |  | Require 50 additional chairs (contingency) | Wen Jun/Suntec
|  |  |  | 3 Microphones - 1 wired & 2 wireless | Wen Jun/Suntec | Need a Rostrum Mic / 1 Wireless for Speaker/ Standing Mic for Audience
|  |  |  | Projector/Screen Required & Signage | Roselyn
| 1400-1700 | Mandarin Workshop | Rm 202 | 2 Speakers | Tan Hwee Yong
|  |  |  | Coffee-Break @ 3:15pm (No. included)* | Wen Jun/Jenny
|  |  |  | Projector/Screen Required & Signage | Roselyn
|  |  |  | 3 Microphones: 2 wireless & 1 standing mike | Wen Jun/Suntec | Need a Rostrum Mic / 1 Wireless for Speaker/ Standing Mic for Audience
|  |  |  | Registration Desk needed | Wen Jun/Suntec
2008-05-23 | 1830-2300hrs | Welcome Night | Ballrooms | "MAD" Theme | Raymond Ho, Sam
|  | Program | 1 & 2 | Banquet Layout inside the Ballrooms. Need 4 spreadout stations | Wen Jun/Suntec
|  |  |  | Mediterranean Theme (No. of pax: 430 + 2 reserves) | Jenny/Angeline
|  |  |  | Need a Registration Desk & Table for Prizes | Wen Jun/Suntec
2008-05-24 | 0830-1200hrs | Opening Ceremony | Theatre | Guest-of-Honour: Speaker of Parliament: Mr Abdullah Tamugi | Aziz Mustajab
|  | Estimated Attendance No. 450 |  | Reserve 1 VIP Car Park Lot at Entrance of Convention Centre | Wen Jun/Suntec
|  | Auditorium Capacity: 596 |  | Require GOH's Vehicle Reg No. SP1 | Aziz Mustajab
|  |  |  | Confirmed Std Package for Audio/Visual 2X @ Theatre | Wen Jun/Felicity of | Need a Rostrum Mic / 2 Wireless Handheld Mics for MC
|  | Entertainment & Performance |  | Rental of Suntec's Projector | Suntec & Jenny
|  |  |  | Registration Desk needed x 2 plus microphones x 3 | Wen Jun/Suntec
|  | Plenary Session by Mr Ed Hearn, |  | Coffee Break @ 10:00am (No. of pax: 420) | Wen Jun/Jenny/Angie
|  | 2006 World Champion Speaker |  | Signage / Projector | Roselyn
| 1200-1330hrs |  |  | Lunch Menu: Singapore Theme (No. of pax: 420 + 2 reserves) | Jenny/Angie/Wen Jun
|  |  |  | Level 3: Concourse | Wen Jun/Suntec
| 1300-1415hrs | General Session with Mr Ed Hearn | Theatre | Registration Desk | Wen Jun/Suntec
| 1430-1745hrs | Mandarin International Speech & | Room 202 | Registration Desk x 2 at Level 3; Exit at Level 2 | Wen Jun/Suntec
|  | Table Topic |  | Mandarin Team will provide own Projector | Tan Hwee Yong
|  |  |  | Need Side Screen, Stage Setup Arrangements, 2 Clip mic, | Wen Jun/Suntec | Need a Rostrum Mic / 1 clip on Wireless for Speaker/ suntec should standby one
|  |  |  | Whyteboard, Holding Room for Contestants | Roselyn
|  |  |  | Coffee Break @ 4:15pm (No.of pax: 460 incl Mandarin Session)* | Jenny/Angie/Wen Jun
| 1330-1730hrs | Tamil Workshop/Contest | Room 203 | Registration Desk | Balasundram, Sithara, | Balasundram no more involved
|  |  |  | Signage, Projector Screen, Stage Setup, std microphone supply | G. Balachandran | 01 x Wireless Lapel (Clip-On)
|  |  |  | Whyteboard, Holding Room for Contestants | Rose | No table topics, so no holding room needed
|  |  |  | Coffee Break @ 3:15pm (No. of pax: 130) | Wen Jun/Suntec
| 1430-1745hrs | Concurrent Workshops |  | Tracks: A - Communication; B - Personal Growth; C - Leadership | John Tan,
|  | Program | 208/209 | D - Club Success | Yeo Chai Toon & | 02 x Wireless Lapel (Clip-On)
|  | Manpower & control. |  | Session 1 - 2:30pm to 3:15pm | Chan Boon Hwee.
|  | Audio/visual equipment |  | Session 2 - 3:30pm to 4:15pm
|  | Ticketing |  | Session 3 - 4:45pm to 5:30pm
|  | Signages |  | Coffee Break @ 4:15 to 4:45pm (No.of Pax: 460 incl Mandarin Session)* | Wen Jun/Suntec
|  | Any other issues? |  | Need Projectors for all Sessions, Signages | Roselyn
|  | Q & A |  | Registration Desks needed for all Rooms | Wen Jun/Suntec
|  |  |  | Microphones x 3, Headtable, Whyteboard, Flip Charts, Markers | Wen Jun/Suntec
|  |  |  | Projection Screens | Wen Jun/Suntec
2008-05-24 | 1830-2300hrs | Gala Dinner & Dance | Ballrooms | "Latino" Theme | Raymond Ho, Sam
|  |  | 1 & 2 | Chinese Dinner & 2 Vegetarian Tables & 1 Muslim Table | Wen Jun/Suntec
|  |  |  | (No. of pax:470 + 2 reserves) | Angeline Koh
|  |  |  | Food Tasting - Feedback | Wen Jun/Suntec &
|  |  |  | Need a table for prizes | Angeline Koh
Wen Jun/Suntec
|  |  |  | Need promotion table for Semi-Convention Marketing & HK Mktg | Wen Jun/Suntec
|  |  |  | Beer Drinking Contest: Cockage fee can it be waived for liquor | Wen Jun/Suntec
|  |  |  | brought in for the Gala Night Dinner? | Jenny Au | Potted plants from Funsgarden. Confirmed. Distr. On Gala Night. Need 2 Tables with Skirting.
2008-05-25 | 0830-1230hrs | Contests & Closing Ceremony | Theatre | 1. English International Speech Contest | Chin Mei Har & Team
|  |  |  | 2. English Table Topic Contest | Goh Wei Khoon
|  |  |  | Coffee Break @ 10:00a.m: Total No. of Pax: 470 | Wen Jun/Suntec | Need a Rostrum Mic / 1 clip on Wireless for Speaker/ suntec should standby one
|  |  |  | Still negotiating for lower price from Suntec | Wen Jun/Suntec &
Jenny
| 1230-1400hrs | Lunch-time program | Concourse | L3 | Wen Jun/Suntec
|  |  |  | Lunch: International Theme & No. of Pax: 450 + 2 reserves | Angeline Koh
|  |  |  | Stage set-up ok at L3 Concourse | Wen Jun/Suntec | Need 2 Wireless or Wired Mic for 2 MC?
|  |  |  | Need a headtable | Roselyn | May have lucky draw for those who submit the evaluation forms.
| 1400-1700hrs | Incoming District Officers Training | Room 208 | New ExCo, etc Meeting | Tay Yiang Ping | Goh Wei Koon in-charge
|  |  |  | Coffee Break @ 4:00pm (No. of Pax: 40) | Wen Jun/Jenny
Volunteers
|  | Ushers Duty Roster |  | Supply volunteers | Yeo Chai Tun
|  |  |  | 6 volunteers needed for both Hospitality at L3 Concourse Lunches | Roselyn/Angeline/
|  |  |  | & Logistics Support. | William/Jenny
Food & Beverage Summary
| 1 | District Meetings Coffee Break |  |  | Jenny Au & the | Need to issue coupons for tea break and Lunch for District Officers
| 2 | Friday's Lunch |  |  | Hospitality Team
| 3 | Friday afternoon's Tea Break
| 4 | Welcome Night
| 5 | Saturday's Coffee Break
| 6 | Saturday's Lunch
| 7 | Saturday's Tea Break
| 8 | Gala Dinner & Dance
| 9 | Sunday's Coffee Break
| 10 | Sunday's Lunch
| 11 | Sunday's Tea Break
| 12 | Any other matters
| 2 | Audio/Visual arrangements |  |  | Logistics Team | Please request Suntec to standby one LCD Projector, in case our loan projector breakdown ( the bulk brow)
| 3 | Signages
| 4 | Stage props (Back drops, Flag-stands etc.)
| 5 | Timing Control |  | Standby additional Timer & Stopwatch for Int'l Contests | Jenny Au | For Contest.. Need to check any colour blind contestant to prepare necessary timing device
| 6 | Any others
Accommodation for Foreign Delegates & Guests
| 1 | Hotel Bencoolen (25 room x 2 = 50pax) & Bayvie Hotel - Booked forAnne Barab/Hubby, Ed Hearn and Neil Sy |  |  | Jenny Au & the
| 2 | Thailand Delegates occupied 8 Rooms @ Bencoolen and 12 Rooms occupied by HK Delegates |  |  | Hospitality Team
| 3 | Arranged bus transportation for overseas delegates; HK & Thailand. 2 Buses @ $80/- per bus. Cost sharing by the delegates.
on Sunday, 25 Jun 08 (Closing Ceremony). Route: 1-way from Hotel Bencoolen to Suntec Convention Centre.
Prepared by: Jenny Au on 13 Apr 08
Updated 03 Jun 08

## F&B
2008 MAD CONVENTION TEAM BUILDING DAY AGENDA.
Food & Beverage. |  | Activity--> | Capacity | A | B | C | D | E | F | G | H | I | J | K | L | M | N
1 | Fri 23 May 08 / Coffee/Tea Break | Rms 208/209 | 309 | A: 10:30a.m.
for District Officers only
| Fri 23 May 08 / Coffee/Tea Break | Rms 208/209 | 309 | B: 3:30p.m.
| Fri 23 May 08 / Coffee/Tea Break | Room 202*MW | 154 | C: 3:15p.m.
2 | Fri 23 May 08 / Lunch, for District Officers+AM Working Committee, actual 70+ as some did not use Lunch vochure | Joachim R. |  | D: 12:30p.m.
4 | Fri 23 May 08 Intl Buffet D'inner (Mediterranean) | Ballrooms 1-2 | 760 | E: 6:30p.m.
5 | Sat 24 May 08 / Coffee/Tea Break | Theatre *OC | 596 | F: 10:00a.m
6 | Sat 24 May 08 / Lunch (Singapore Theme) | L3 East Gallery |  | G: 12:00p.m.
7 | Sat 24 May 08 / Coffee/Tea Break | Rms 208*B | 158 | H: 4:15p.m.
| Sat 24 May 08 / Coffee/Tea Break | Rms 209*B | 151
| Sat 24 May 08 / Coffee/Tea Break | Rms 202*B | 154
| Sat 24 May 08 / Coffee/Tea Break | Theatre*M | 596 | I: 4:00p.m.
| Sat 24 May 08 / Coffee/Tea Break | Room 203*T | 194 | J: 3:15p.m.
8 | Sat 24 May 08 / Chinese Dinner & Special Order | Ballrooms 1-2 | 760 | K: 7:00p.m.
9 | Sun 25 May 08 / Coffee/Tea Break | Theatre | 596 | L: 10:00a.m.
10 | Sun 25 May 08 / Lunch (International Theme) | Ballrooms 1-2 |  | M: 12:30p.m.
11 | Sun 25 May 08 / Coffee/Tea Break | Room 204 | 56 | N: 3:30p.m.
Other | Estimated No. of attendees for each session |  |  | 60 | 300 | 150 | 60 | 450 | 440 | 440 | 380 | 100 | 150 | 480 | 500 | 500 | 50
| F&B Catering Numbers (actual) |  |  | 60 | 350 |  | 60 | 430 | 420 | 420 | 460 |  | 130 | 470 | 470 | 450 | 40
Info | Secretariat Room available from 22-25 May
Issue meal coupons for crowd control
Need to know #s Muslim & Chinese Vegetarian menu (based on 10 guests seating arrangements on 24 May)
Dinner Menu package includes free flow of soft drinks only. (Juices, Beer & Others are chargeable on pax account.)
All Coffee/Tea Breaks will either be at the Foyer or Outside the Meeting Rooms
Legend: A: | A: District 80 Exco & Council Meeting | F: Opening Day of District 80 Annual Convention |  | F: K: Latino Gala Dinner & Dance
| B: Anne Barab's Session | G: Convention Lunch |  | F: L: International Speech & Table Topic contests
| C: Mandarin Workshop | H: Breakout Sessions |  | F: M: Farewell Lunch for All Convention Delegates
| D: Exco, Council & Appointment Holders Only | I: Mandarin International Speech & Table Topic Contests |  | F: N: Incoming District Officers Training
| E: Welcome Night | J: Tamil Workshop / Contest
AV Package for all Meeting Rooms/Theatre |  | Chargeable for additional equipment: |  | A: Audio/Visual Special Package for the Theatre (Use for 2 days: 24 & 25 May)
- Use for 3 days (23, 24 & 25 May 2008) |  | - Wireless Handheld microphone |  | D: - Full lighting in the room & stage
- Full lighting in the room and stage |  | - Wireless Click-on/Lapel microphone |  | D: - Podium + microphone x 1 unit
- Podium & microphones x 1 unit |  | - Wired Handheld microphone |  | D: - Handheld microphone x 1 unit
- Wired Handheld microphone x 1 unit |  | - LCD Projector (Meeting Room) |  | D: - Wireless microphone x 1 unit
- Wireless microphone x 1 unit |  |  |  | D: Rate: S$1,800.00
- Standing microphone x 1 unit
Presented by: The Hospitality Team (Jenny Au/Angeline Koh/William Tang)