DISTRICT 80 ANNUAL TOASTMASTERS CONVENTION 2008

ORGANISING COMMITTEE

NOTES OF THE DEBRIEF with emphasis on AREAS FOR IMPROVEMENT

| Date of Meeting | : | 26 June 2008 |
| --- | --- | --- |
| Time of Meeting | : | 4.30pm |
| Place of Meeting | : | Roland Restaurant, 89 Marine Parade Central Level 6, Private Function Room, Singapore |

Attendance

|  | MAD Team |  | Present |
| --- | --- | --- | --- |
| 1 | Tay Yiang Ping DTM | Organising Chair | * |
| 2 | Michael Rodrigues DTM | Co-Organising Chair | * |
| 3 | Monica Goh | Treasurer |  |
| 4 | Chin Mei Har | Closing Ceremony Chair /Secretary | * |
| 5 | Dayal Khemlani | Closing Ceremony | * |
| 6 | Elizabeth Thorarajoo | Closing Ceremony |  |
| 7 | Goh Kheng Chuan | Closing Ceremony |  |
| 8 | Liu Ji Yin | Closing Ceremony | * |
| 9 | Golam Hossain | Closing Ceremony | * |
| 10 | James Lim DTM | Closing Ceremony | * |
| 11 | Joanne Koo | Closing Ceremony |  |
| 12 | Ng Cher Khim | Closing Ceremony | * |
| 13 | John Tan | Educational Program Chair | * |
| 14 | James Tan | Educational Program | * |
| 15 | Yeo Chai Tun DTM | Educational Program | * |
| 16 | Chan Boon Hwee DTM | Educational Program | * |
| 17 | Kris Tay | Editorial Chair / Publication | * |
| 18 | Albert Lim DTM | Editorial | * |
| 19 | Cheng Chia Yi | Editorial | * |
| 20 | Edward Ma | Editorial | * |
| 21 | Lynda Neo | Editorial | * |
| 22 | Ryan Lim | Webmaster |  |
| 23 | Chris Yam | Publication Advisor |  |
| 24 | Jenny Au | Hospitality Chair | * |
| 25 | Angeline Koh | Hospitality | * |
| 26 | William Tang | Hospitality | * |
| 27 | Rose Ho | Logistic Chair | * |
| 28 | Amy Ng Min Yin | Logistic / Hospitality | * |
| 29 | Heru Adi Kusuma | Logistic | * |
| 30 | Winson Lim Wee Sing | Logistic |  |
| 31 | Aziz Mustajab DTM | Opening Ceremony Chair | * |
| 32 | Ashley He | Opening Ceremony |  |
| 33 | Esther Heng | Opening Ceremony | * |
| 34 | Ken Toh | Opening Ceremony |  |
| 35 | Laksha Mehta | Opening Ceremony |  |
| 36 | Ruby Lai | Opening Ceremony | * |
| 37 | Doreen Neo | Secretariat Chair | * |
| 38 | Grace Tan | Secretariat |  |
| 39 | Kong Pak Fee | Secretariat | * |
| 40 | Tay Tiam Teang | Secretariat | * |
| 41 | Ang Soh Hwa | Secretariat | * |
| 42 | Edwin Seah | Secretariat |  |
| 43 | Poh Yeow Kian | Secretariat |  |
| 44 | Sam Chee Yee | Welcome Nite /Gala Dinner Chair | * |
| 45 | Raymond Ho | Welcome Nite /Gala Dinner Chair | * |
| 46 | Chee Kim Loon | Welcome Nite /Gala Dinner | * |
| 47 | Eng Zee Lin | Welcome Nite /Gala Dinner | * |
| 48 | Jeshua Solomon Juda | Welcome Nite /Gala Dinner |  |
| 49 | Lora Lee | Welcome Nite /Gala Dinner |  |
| 50 | David Liem | Welcome Nite /Gala Dinner |  |
| 51 | Lily Lim | Welcome Nite /Gala Dinner |  |
| 52 | Catherine Goh | Welcome Nite /Gala Dinner | * |
| 53 | Lim Bee Bee | Welcome Nite /Gala Dinner |  |
| 54 | Kenneth Wee | Welcome Nite /Gala Dinner |  |
| 55 | Brennan Khor | Welcome Nite /Gala Dinner |  |
| Mandarin Programme |  |
| 56 | Tan Hwee Yong | Mandarin Programme Chair | * |
| 57 | Seah Min Choo | Mandarin Programme | * |
| 58 | William Tay DTM | Mandarin Programme |  |
| Tamil Progarmme |  |
| 59 | G. Balachandran | Tamil Programme Chair | * |
| 60 | Harikrishnan | Tamil Programme |  |
| 61 | Brahmakumar DTM | Tamil Programme | * |
| 62 | Sithara Dorisasamy | Tamil Programme |  |
| 63 | Manivannan | Tamil Programme | * |
| Top District Officers 2006-2008 |  |
| 64 | Michael Wee DTM | Advisor | * |
| 65 | Goh Wei Koon DTM | Advisor | * |
| 66 | Neil Sy ACB CL | Advisor |  |
| 67 | Poh Kim Siong DTM | Advisor | * |
| 68 | Dr Khong Chooi Peng DTM | Advisor |  |
| 69 | Gea Ban Peng DTM | Advisor | * |
| Others |
|  | Roy Ong How Kah Hee David Kow |  | * * |
|  |  |  | * |
|  | Lim Ang Chew |  | * |
|  | Lim Jit Koon |  | * |
|  | Er Hwee Meng |  | * |
|  | Lim Poh Kim |  | * |
|  | Chua Chwee Hoon |  | * |
|  | How Yong Chin |  | * |
|  | Amy Chua Chor Eng |  | * |
|  | Lim Meng Khng |  | * |
|  | William Lim |  | * |
| Item | Subject | By |
| 1.0 | Welcome Address by YP YP thanked members and helpers for making time and effort to attend the debrief . | YP |
| 2.0 | Report from the Organising Chair Evaluation Report in Pie Chart (please see attachment) YP gave a general assessment of the evaluation submitted. About 35% of the delegates submitted the feedback. 3 Main Reasons for signing up for the Convention Popularity of Keynote speaker, Ed Hearn. To attend International Speech Contest To network Using Suntec City Convention Hall was an excellent decision as seen in The feedback. | Tay Yiang Ping |
| 3.0 | Report from the Secretariat The deadline given by the printer should be closely adhered to. Key information for the delegates should be available especially about any changes in workshops. The First Aid Box should be provided, especially with new items. Announcement of Safety Evacuation should be observed. Frequency of Announcement of Lost Items should be carried out. Agency for selling of products of the speakers to be better organized. Feedback received: DG Michael felt there should be feedback after every event instead of only having one evaluation spanning all the events. Manivannan gave the opinion that speakers should inform Secretariat beforehand if they so wished to sell products. | Doeen Neo DG Michael Manivannan |
| 4.0 | Report from Logistics There should be 5 full members in the team. Two ad hoc members to be on duty on convention days. Event chairs should submit Logistics requirement list in advance and should not change their request as far as possible. Event chairs should work within the constraint of the standard provision of items given as a package by Suntec City Mgt. The total of flags required for the Opening Ceremony must be kept together and there must be accountability and proper handing over to the next convention chair. | Rose Ho |
| 5.0 | Report from Hospitality Logistics & Hospitality teams should be combined as one department as there was a lot of overlapping of duties especially in liaising with Suntec City’s personnel. Logistics members should be asked by Event Chairs to attend their meetings if they were to discuss about equipment and logistics. Overseas Representatives of the delegates should take greater ownership of their duties and give prompt email replies so that not so much time, effort and means be spent on telephone calls. Changes in hotel plans of the delegates should be promptly reported by overseas representatives for efficient communication with the hoteliers by the Hospitality Head. Feedback and comments received: Singapore toastmasters should host 2010 Toastmasters International Convention and the venue: Integrated Resorts. Concerted effort by the Hospitality Team to ensure that overseas delegates are welcome at the airport. Ushering of delegates to their dinner seats should be arranged. The whole organizing committee should play host at the dinners. | Jenny Au John Tan DG Michael YP Heru |
| 6.0 | Report from the Editorial Articles and messages should be submitted on time. Advertisements received should be in portrait format not landscape. Resolutions of these advertisements should be better. It could have been better if announcement of the essay competition had been done earlier. | Kris Tay |
| 7.0 | Report from Education & Training The online registration of workshops was useful and there was no complaint from delegates in this area. Need to have a clause that the workshops are subject to change for e.g., Gerald Green’s cancellation of workshop. Delegates attending Kelvin Ong’s first workshop did not know that he was given 2 hours to conduct his workshop. Announcement should be made in the Auditorium prior to the workshop. It might be a good idea to have workshops of different duration. Feedback received: Ed Hearn only delivered 30 minutes speech at Opening, though he knew that the duration was 1 hour 15 mins DG asked if we should allocate Ed Hearn to speak on crafting a winning speech. Kris and some who attended the Dialogue session said, he did share his experience with the delegates. | John Tan |
| 8.0 | Report on the Mandarin Speech Contest & Workshop Certificates of better quality was requested and YP would followup with LGET that this is carried out. | Tan Hwee Yong |
| 9.0 | Report on Tamil Speech Contest & Workshop This was the world’s first Toastmasters Tamil Speech Contest & Workshop. It might be difficult to have a Tamil Speech contest in another country in District 80 owing to a lack of the critical mass of Tamil ethnic group in Thailand, Hongkong and Macau for such a contest to be viable. Request was also made to exchange the thin quality of the certificates for better quality ones. | Manivannan Rose Ho |
| 10.0 | Report on the Opening Ceremony It is essential for flag bearers to practise bearing the flag before the Opening Ceremony in the early morning, so that they were there earlier, also to greet Guest of Honour when he arrived | Aziz Mustajab |
| 11.0 | Report from the Welcome/ Gala Dinner Committee Having a keynote speaker at the Gala dinner might not be such a good idea after all. | Sam Chee Yee |
| 12.0 | Report from Contests & Closing Ceremony/ Farewell Lunch Committee The slip of paper with the table topic statement should be given to contestants to read after the Contest Chair had read out the topic. This would eliminate any misunderstanding of pronunciation of key word/s. Closing ceremony could have been less ‘draggy’ (as described in the Evaluation form) if the drummers roped in for the Promotion of the next convention had adhered to the time given. Feedback received: Co-chair commented that we should learn from one another as mentioned by Mei Har who thanked Amanda of the previous Hongkong Convention who provided the ‘blue print’ for the Contest & Closing Ceremony and Aziz Mustajab for the Logistics Checklist. | Chin Mei Har |
| 13.0 | Report from Head of the Volunteers There were a few difficult cases and the lesson learnt was we have to stand up for what is right but to speak in a diplomatic and gentle but firm tone to delegates who had exceeded their rights. Delegates should not reserve the seats for others unless they were very sure that he or she would turn up. | Yeo Chai Tun Voiced by several members |
| 14.0 | Closing Address by DG Michael Wee The Organising Committee of the MAD Convention had set a standard for other conventions to adopt and model after. | DG Michael |
| 15.0 | Conclusion by Organising Chair The MAD Convention Organising Committee had done ‘exceptionally well.’ We will prepare all Reports to pass to the future convention organising chairs: Nov 2008 Singapore, May 2009 Hong Kong and May 2010 Thailand. | Tay Yiang Ping |
| 16.0 | There being no other business, the debrief was concluded at 7.10pm and was followed by The MAD Convention Appreciation Dinner |  |

Reported by

MAD Secretary

Chin Mei Har

Vetted by

Organising Chair

Tay Yiang Ping

Submitted on

3 July 2008