DISTRICT 80 ANNUAL TOASTMASTERS CONVENTION 2008

ORGANISING COMMITTEE

MINUTES OF MEETING NO. 10

| Date of Meeting | : | 20 Feb 2008 |
| --- | --- | --- |
| Time of Meeting | : | 8.00pm |
| Place of Meeting | : | Toa Payoh Central CC, Level 3 Mini theatre |

Attendance

| MAD Team |  |  | Present |
| --- | --- | --- | --- |
| 1 | Tay Yiang Ping | Chair | * |
| 2 | Mike Rodrigues | Co-Chair | * |
| 3 | Monica Goh | Treasurer |  |
| 4 | Ryan Lim | Webmaster/Closing |  |
| 5 | Chris Yam | Printer | * |
| 6 | Chin Mei Har | Closing/Secretary | * |
| 7 | Dayal Khemlani | Closing |  |
| 8 | Elizabeth Thorarajo | Closing |  |
| 9 | Goh Kheng Chuan | Closing |  |
| 10 | Liu Ji Yin | Closing | * |
| 11 | Golam Hossain | Closing |  |
| 12 | James Lim | Closing |  |
| 13 | Joanne Koo | Closing |  |
| 14 | John Tan | E&T |  |
| 15 | James Tan | E&T | * |
| 16 | Yeo Chai Tun | E&T | * |
| 17 | Chan Boon Hwee | E&T | * |
| 18 | Kris Tay | Editorial | * |
| 19 | Albert Lim | Editorial |  |
| 20 | Cheng Chia Yi | Editorial |  |
| 21 | Edward Ma | Editorial |  |
| 22 | Jenny Au | Hospitality | * |
| 23 | Angeline Koh | Hospitality | * |
| 24 | William Tang | Hospitality |  |
| 25 | Rose Ho | Logistic |  |
| 26 | Amy Ng Min Yin | Logistic |  |
| 27 | Heru Adi Kusuma | Logistic |  |
| 28 | John Choi | Logistic |  |
| 29 | Winson Lim Wee Sing | Logistic |  |
| 30 | Aziz Mustajab | Opening | * |
| 31 | Ashley He | Opening |  |
| 32 | Esther Heng | Opening |  |
| 33 | Ken Toh | Opening |  |
| 34 | Laksha Mehta | Opening |  |
| 35 | Lynda Neo | Opening | * |
| 36 | Raja Kumar | Opening |  |
| 37 | Ruby Lai | Opening | * |
| 38 | Doreen Neo | Secretariat | * |
| 39 | Grace Tan | Secretariat |  |
| 40 | Kong Pak Fee | Secretariat | * |
| 41 | Tay Tiam Teang | Secretariat | * |
| 42 | Ang Soh Hwa, Ashley | Secretariat | * |
| 43 | Chan Siew Peng (Esther) | Secretariat |  |
| 44 | Edwin Seah | Secretariat |  |
| 45 | Raymond Ho | Welcome/Gala |  |
| 46 | Sam Chee Yee | Welcome/Gala |  |
| 47 | Chee Kim Loon | Welcome/Gala |  |
| 48 | Eng Zee Lin | Welcome/Gala |  |
| 49 | Jeshua Solomon Judah | Welcome/Gala |  |
| 50 | Lora Lee | Welcome/Gala |  |
| 51 | David Liem | Welcome/Gala |  |
| 52 | Lily Lim | Welcome/Gala |  |
| 53 | Catherine Goh | Welcome/Gala |  |
| 54 | Lim Bee Bee | Welcome/Gala |  |
| Mandarin Programme |  |  |  |
| 55 | Seah Min Choo |  |  |
| 56 | Tay Lai Huat |  |  |
| Tamil Progarmme |  |  |  |
| 57 | Balasundaram |  |  |
| 58 | G. Balachandran |  |  |
| 59 | Sithara |  |  |
| Top District Officers |  |  |  |
|  | Michael Wee |  | * |
|  | Goh Wei Koon |  |  |

| Item | #### Subject | #### Action |
| --- | --- | --- |
| 1.0 | Welcome Address by YP YP thanked members for making time and effort to attend 10th meeting. | Info |
| 2.0 | Time Schedule YP reported that so far the schedule has been on time. - Only three critical months left before our MAD Convention. - Two meetings will be scheduled in March, they will be replaced by Team Building on 23 Mar, Sunday, 1-6pm - Advertisements have to be confirmed and artwork submitted by end February. Lynda Neo is in charge of liaising with the advertisers. - By April, we have to pay up 80% of the charges to Suntec City. - Convention Registration will be closed by 29th February. - Events tickets will be on sales by 1st March with tickets ready soon. | All |
| 2.1 | Account/Sale Update On behalf of the MAD Treasurer, Monica, YP went over the accounts. MAD Team were urged to contact those in their clubs who have yet to pay for their tickets. Total sales todate – 450, many still without names.. Khanita from Thailand will represent the Thai delegates. 20 tickets have been set aside for Thai toastmasters. Presently, $33,000 in cash and kind have been pledged. | YPl |
| 3.0 | Early Bird Lucky Draw District Governor, Michael Wee, DTM, did the honour of picking the three lucky winners of the Night Safari tour donated by Monica Goh. The three lucky winners: - Lim Ang Chew of Division L - Katherine Tan Ah Neo of Division B - William Tang of Division D | MG |
|  | MAD Team Leaders’ Presentation |  |
| 4.0 4.1 4.2 | Hospitality Team Jenny reported that a total of 20 hotels had been contacted for the rates. The average cost is 250/- per night per room. Conrad Hotel: $250/-++ Hotel Bencoolen $118 to $128/-net Strand Hotel and Bayview Hotel: about $160/- Jenny will sending out information to the overseas delegates to book hotel rooms on their own. | JA |
| 5.0 | Opening Ceremony- Saturday, 24 May 08 - Lion Dance to welcome the Guest of Honour Abdullah at 8.45am. - Rose Ho will be sourcing for Lion Dance troupe. - There shall be 3 Speakers only. - Cheng Jia Yi shall escort DG Michael Wee up the stage. - Division Governor has the honour of declaring the Convention opened. However, he will demonstrate the courtesy of inviting the Guest to perform the honourable act with him - To form the March In, Aziz will contact directly with the all officials to be ready at Theatre and those who carrying flags. - Raja will be working with the Suntec technicians concerning the AV System. - The Sitting Arrangement can be a sensitive issue. Aziz will work with YP and MW, Logistic will then follow up to prepare the labels. | Aziz RH |
| 6.0 | Food & Beverage Tea Break- 3 snack items is preferred, but it cost $14.16 w GST. AK to ensure that the quantity is sufficient and may be consider 2 snack items in 1-2 Tea Breaks. Fri, 23 May Lunch –Suntec Porridge for District Officers, Volunteers & MAD Working Team Dinner- International Buffet Saturday, 24 May Lunch – Singapore Style Dinner – Chinese sit down dinner Sunday, 25 May Lunch - Mediterranean Cuisine | AK |
| 7.0 | MAD Convention Workshops -45min in duration General Session – 1.30-2.15pm (Ed Hearn) Other workshops by 8 Speakers 1 2.30 – 3.15pm 2 3.30 – 4.15pm Tea Break at 4.15-4.45pm - 4.45-5.30pm To facilitate smooth running of workshops, the following suggestions were made: - On-line Registration of Workshops in early April - Remainder will make Booking of workshops during Registration | E&T |
| 8.0 | Pricing for Single Events Tickets A Welcome Night / Gala Dinner - $98/- each B Contest cum Farewell Lunch $80/- A+B= S160/- |  |
|  | The meeting ended at 10.05pm. |  |

Minutes recorded by MAD_SEC Chin Mei Har, submitted on Monday, 251 Feb 08 at 3.40pm.

Vetted by OC Tay Yiang Ping and COC Michael Rodrigues