2nd meeting n 5 May 08

As the days were drawing nearer, the secretariat team met to discuss the progress of each area of responsibility.

1	Convention Bag

a)	Logo position

Doreen showed the team members a sample of the bag to comment the position of the MAD logo and the IMAGNIT logo.

i) MAD logo on the front side left hand corner when holding the bag facing you.

ii) similar to IMAGINIT logo

2	Name Tag

a) 	Members of District 80 – as previously discussed, an icon to represent each country

i) Junk Boat -  Hongkong

ii) St Paul Ruins – Macau

iii) Temple – Thailand

iv) Merlion – Singapore

v)  World map – outsider Dist 80

b) 	Printing Info on Name Tag

i) Name & Division

ii) Icon

iii) MAD log

c)	Speaker’s Name Tag

i) Name

ii) Photo

iii) Speaker

iv) MAD logo

d) 	Sponsor

i) Company’s Name

ii) Sponsor

iii) MAD logo

To obtain sponsor’s list from YP

e)	Event holder

i) No Name Tag needed – they produced ticket

f) 	Lanyard

i) delegates, speakers, sponsors and top officials – navy blue

ii) committee - orange

3	Useful contacts Number

a)	To be printed on the reverse side of the name tag

b)	Contact

1) organizing Chair - YP

2)  organizing co-Chair – Michael Rod

3) Secretariat Members

4) Hospitality – Jenny

5) Logistic

6) Taxi

i) comfort

ii) Smart

7) Emergency Number

i) 999

ii) 995

4	Program/Floor plan

a) to get from the confirmed workshop venue/time for printer

b) floor plan

5)	Coupons

a) Is it necessary to have coupons for admission to various events

when Name Tag could be used. To get YP’s approval

b) Breakout Sessions

i) Concurrently 8 workshops

ii) who to manage the online registration

Doreen will do the initial contacts with printer on the designs for the various items. After everything being firmed up, TT would follow up with the printer.

6) Packing

a)	Pak Fee is in charge of the Packing.

b) 	No. of helpers close to 30 of wh attempt to get from RSVP 15

c)	Goods to arrive at Suntec by 11.30 am latest

d)	Packing of bag and lanyard to be carried out concurrently

e)	Room layout – to revisit suntec – Doreen to arrange

f)	Suggestion to seek Kok Hwa’s help in loading & unloading the “goods

wHwa

(post note: Chai Tun cld only get about 5 – 6 pax from RSVP to help in the packing)

7) Delegate List

a)  Members felt that it was not necessary to have serial number printed on the Name Tag if the process worked fine.

b) TT to liaise and follow up with Treasurer (monica) and web master for the delegate list

c) Also liaise with Ryan & Chai Tun on the preparation of pre-registration for workshop

d) Doreen to do the initial negotiation with printer. Subsequent follows up nearing to the date to be done by TT with printer. Printer needs 4-5 days for printing.

e) one copy of Control list & few working list with information like Name, Division, Club

8) Registration Counter

a) Ashley would take charge

b) Plan Roster & work flow

i) Division H, K, T including speaker/sponsor

ii) Division L

iii) Division D

iv) Division B

v) Division S, U, Z

c) No. of helpers – 15 from RSVP

(post meeting note: Chai Tun only able to get abt 4-5 helpers)

9) Workshop Registration

a) at this point it was not clear as to who would be manning the Workshop c Reg counter, Yeow Kian to  take charge

b) 1 key personnel from E&T

c) 3 counters since there are 3 different slots

d) to get pre-registration list before day of packing so that the coupons of choice could be inserted into the delegate Name Tag

10) Mandarin Workshop

a)  To clarify in the coming meeting.

11) Signage

a) the necessary signage to be prepared by TT

b) printing by Secretariat

12) Parking Coupons

a) Jenny would provide the number

b) coupon is per entry

c) to check for committee any multiple entries.

Recorded by Doreen