## Sheet1
Month | 2007-01-01 | 2007-02-01 | 2007-03-01 | 2007-04-01 | 2007-05-01 | 2007-06-01 | 2007-07-01 | 2007-08-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2007-12-01 | 2008-01-01 | 2008-02-01 | 2008-03-01 | 2008-04-01 | 2008-05-01
Confirmed Main Committee | 2008-03-01: Team Buidling
Confirmed Sub-Committee | 2007-01-01: Select Sub-Committee; 2007-06-01: Invite all Divisions as Sale and Marketing (DOT / COT); 2007-10-01: Divisions Contest; 2007-12-01: 2nd COT / Pre-Convention Workshop; 2008-03-01: Event Sales
Committee Meeting |  | 1st | 2nd | 3rd | 4th | Holiday | 5th | 6th | Holiday | 7th | 8th | Holiday | 9th | 10th | 11/12th | 13/14th | 15/16th
Publicity | 2007-03-01: Confirm Venue Package / Flyers /Banner / Website; 2007-04-01: Sales / Marketing Planning; 2007-05-01: HK Promo; 2007-06-01: Light Promotion; 2007-11-01: S'pore Promo; 2007-12-01: Aggressive Promotion
LGET letter
Enrolment | 2007-04-01: 65% µ; 2008-02-01: 100%; 2008-03-01: Registration Event Only
Budget | 2007-02-01: Budget Plan; 2007-04-01: Budget Review; 2007-07-01: Account update; 2008-02-01: Account update; 2008-05-01: Account update
Venue Payment | 2007-06-01: 1st Deposit (20%); 2007-12-01: 2nd Deposit (40%); 2008-04-01: 3rd Deposit (40%); 2008-05-01: Final Settlement
Invitation/Confirmed GOH and World Champion Speaker | 2007-09-01: Confirmed GOH / World Champion Speaker
Confirmed Speakers | 2007-09-01: Confirmed Workshop Speakers
Registration Participants | 2007-04-01: Committee to signup; 2007-06-01: Participants and Payment; 2008-04-01: Finalise Payment
Programme | 2007-11-01: Draft Program; 2008-01-01: Final; 2008-02-01: All Events Program; 2008-04-01: Pre-Registration
Sponsorship | 2007-03-01: Confirmed Major Sponsors (1 year publicity); 2007-05-01: More Sponsors
Arrangement for Plaque for VIP and Speakers | 2008-04-01: Plaques ready
Secretariat | 2008-02-01: Badges / Bags / Secretariat
Handbook | 2007-09-01: Theme / Collection of Articles / Design layout; 2008-03-01: Editing; 2008-04-01: Printing; 2008-05-01: Done
Advertisement of Handbook | 2008-01-01: Collection of Advertisement
Hospitality | 2008-02-01: Hotel Ready for Booking; 2008-04-01: Food Choice
Stage Preparation | 2008-04-01: Trial Run; 2008-05-01: Trial Run
- Stage Backdrop | bar: 2008-04-01 to 2008-05-01
VCD Player / Recording | bar: 2008-04-01 to 2008-05-01
Logistic | 2008-02-01: Logistic